## Sheet1
LGIP ID (1) | Map reference | Suburb | Project description | Project type | Estimated year of completion (2) | Service catchment | Area of land (hectares) | Establishment cost ($) (3)
ACR-U1-001 | PCF272 | Acacia Ridge | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT OUTDOOR SPORT & DISTRICT GENERAL RECREATION) | Park upgrade | 2026 - 2031 | South | 20.43 | 2829000
AGR-A1-002 | PCF313 | Algester | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | South | 0.2 | 998002
AGR-A1-003 | PCF313 | Algester | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | South | 0.7 | 1508356
AGR-U3-001 | PCF333 | Algester | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION) | Park upgrade | 2031 - 2036 | South | 0.2 | 1476000
ALB-A1-002 | PCF153 | Albion | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | North | 0.13 | 1842661
ALD-U1-001 | PCF132 | Alderley | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT GENERAL RECREATION) | Park upgrade | 2021 - 2026 | West | 5.55 | 2644500
ALD-U3-001 | PCF151 | Alderley | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT NATURE RECREATION & LOCAL GENERAL RECREATION) | Park upgrade | 2026 - 2031 | West | 5.738 | 1414500
ANS-U3-001 | PCF247 | Anstead | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT VISITOR NODE) | Park upgrade | 2021 - 2026 | West | 7.8 | 1322250
ASC-A1-002 | PCF154 | Ascot | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | North | 0.5 | 2185131
ASC-A1-003 | PCF154 | Ascot | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | North | 1 | 6587206
ASP-A1-001 | PCF92 | Aspley | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | North | 0.504 | 9103694
ASP-A8-002 | PCF92 | Aspley | Acquire and embellish land to provide DISTRICT ACCESS/ RECREATION CORRIDOR infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | West | 0.3 | 157436
AUC-U3-001 | PCF191 | Auchenflower | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT URBAN NEIGHBOURHOOD) | Park upgrade | 2031 - 2036 | West | 1.4 | 1476000
BDL-U3-001 | PCF94 | Boondall | Upgrade existing park infrastructure to the value of up to $1m (LOCAL OUTDOOR SPORT) | Park upgrade | 2026 - 2031 | North | 0.3 | 1414500
BFD-E11-001 | PCF169 | Brookfield | Embellish with DISTRICT VISITOR NODE infrastructure | Park Embellishment | 2031 - 2036 | West | 1 | 4469281
BFD-E12-001 | PCF169 | Brookfield | Embellish with METROPOLITAN NATURE RECREATION infrastructure | Park Embellishment | 2021 - 2026 | West | 14.297 | 3933844
BHI-E12-001 | PCF52 | Bald Hills | Embellish with DISTRICT NATURE RECREATION infrastructure | Park Embellishment | 2026 - 2031 | North | 12.2 | 2764751
BNE-U1-001 | PCF193 | Brisbane City | Upgrade existing park infrastructure to the value of $2m+ (METROPOLITAN BOTANIC GARDEN/ ARBORETUM) | Park upgrade | 2026 - 2031 | West | 16.69 | 2829000
BRD-A1-003 | PCF71 | Bridgeman Downs | Acquire and embellish land to provide LOCAL GENERAL RECREATION (& LOCAL OUTDOOR SPORT) infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | West | 0.8 | 2248259
BRD-A1-004 | PCF92 | Bridgeman Downs | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | West | 0.8 | 3566851
BRD-A1-005 | PCF91 | Bridgeman Downs | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | West | 0.4 | 1533831
BRD-A2-001 | PCF71 | Bridgeman Downs | Acquire and embellish land to provide DISTRICT GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | West | 3.318 | 20141076
BRD-U2-001 | PCF72 | Bridgeman Downs | Upgrade existing park infrastructure to the value of $1-2m (LOCAL GENERAL RECREATION) | Park upgrade | 2021 - 2026 | West | 1.6 | 1983375
BRD-U2-002 | PCF91 | Bridgeman Downs | Upgrade existing park infrastructure to the value of $1-2m (LOCAL GENERAL RECREATION) | Park upgrade | 2031 - 2036 | West | 1.53 | 2214000
BRD-U3-001 | PCF91 | Bridgeman Downs | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION) | Park upgrade | 2021 - 2026 | West | 0.4 | 1322250
BRD-U3-002 | PCF91 | Bridgeman Downs | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION) | Park upgrade | 2026 - 2031 | West | 0.16 | 1414500
BRG-A1-001 | PCF53 | Bracken Ridge | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | North | 0.2 | 1241785
BRI-U3-001 | PCF34 | Brighton | Upgrade existing park infrastructure to the value of up to $1m (METROPOLITAN ACCESS/ RECREATION CORRIDOR & METROPOLITAN GENERAL RECREATION) | Park upgrade | 2026 - 2031 | North | 0.6 | 1414500
BUL-A1-001 | PCF174 | Bulimba | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | East | 0.8 | 13248259
BUL-A8-001 | PCF153, PCF154, PCF173, PCF174 | Bulimba | Acquire and embellish land to provide DISTRICT ACCESS/ RECREATION CORRIDOR infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | East | 0.2 | 4104632
BUL-A8-010 | PCF174 | Bulimba | Acquire and embellish land to provide METROPOLITAN ACCESS/ RECREATION CORRIDOR infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | East | 2.6 | 28214146
BUR-E11-001 | PCF256 | Burbank | Embellish with DISTRICT VISITOR NODE infrastructure | Park Embellishment | 2031 - 2036 | East | 1 | 4469281
BUR-E12-001 | PCF256 | Burbank | Embellish with DISTRICT NATURE RECREATION infrastructure | Park Embellishment | 2031 - 2036 | East | 22.542 | 2884957
BUR-U3-001 | PCF257 | Burbank | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT VISITOR NODE) | Park upgrade | 2026 - 2031 | East | 0.92 | 1414500
BUR-U3-002 | PCF277 | Burbank | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT VISITOR NODE & DISTRICT NATURE RECREATION) | Park upgrade | 2026 - 2031 | East | 21.81 | 1414500
BWE-U3-001 | PCF267 | Bellbowrie | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT GENERAL RECREATION) | Park upgrade | 2021 - 2026 | West | 4.54 | 1322250
BYO-A1-001 | PCF114 | Banyo | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | North | 0.8 | 3648259
CAH-U3-001 | PCF214 | Camp Hill | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT GENERAL RECREATION) | Park upgrade | 2021 - 2026 | East | 3.58 | 1322250
CAR-A1-001 | PCF215 | Carina | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | East | 0.5 | 1036318
CAR-A1-002 | PCF195 | Carina | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | East | 0.4856 | 9091334
CDE-U3-001 | PCF72 | Carseldine | Upgrade existing park infrastructure to the value of up to $1m (LOCAL OUTDOOR SPORT) | Park upgrade | 2031 - 2036 | West | 0.3 | 1476000
CDE-U3-010 | PCF72 | Carseldine | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION & LOCAL OUTDOOR SPORT) | Park upgrade | 2021 - 2026 | North | 1.4 | 1322250
CHE-E1-001 | PCF112 | Chermside | Embellish with LOCAL GENERAL RECREATION infrastructure | Park Embellishment | 2031 - 2036 | West | 0.77 | 883082
CHE-U2-002 | PCF112 | Chermside | Upgrade existing park infrastructure to the value of $1-2m (LOCAL GENERAL RECREATION) | Park upgrade | 2031 - 2036 | West | 0.35 | 2214000
CHE-U3-001 | PCF112 | Chermside | Upgrade existing park infrastructure to the value of up to $1m (LOCAL OUTDOOR SPORT & LOCAL GENERAL RECREATION) | Park upgrade | 2031 - 2036 | West | 1 | 1476000
CHE-U3-002 | PCF113 | Chermside | Upgrade existing park infrastructure to the value of up to $1m (LOCAL OUTDOOR SPORT & DISTRICT GENERAL RECREATION) | Park upgrade | 2026 - 2031 | North | 3 | 1414500
CHL-U2-001 | PCF230 | Chapel Hill | Upgrade existing park infrastructure to the value of $1-2m (DISTRICT OUTDOOR SPORT) | Park upgrade | 2021 - 2026 | West | 7.7 | 1983375
CHL-U3-001 | PCF210 | Chapel Hill | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION) | Park upgrade | 2026 - 2031 | West | 2.5 | 1414500
CHW-U3-001 | PCF112 | Chermside West | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT VISITOR NODE) | Park upgrade | 2031 - 2036 | West | 1.86 | 1476000
CLF-A1-001 | PCF133 | Clayfield | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | North | 0.09 | 2899590
CLF-A1-002 | PCF153 | Clayfield | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | North | 0.2179 | 6873526
CLL-A1-001 | PCF195 | Cannon Hill | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | East | 0.25 | 2956691
CLL-A1-010 | PCF195 | Cannon Hill | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | East | 0.16 | 2981714
COO-U3-001 | PCF213 | Coorparoo | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT GENERAL RECREATION) | Park upgrade | 2021 - 2026 | East | 1.7 | 1322250
COO-U3-002 | PCF213 | Coorparoo | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION & LOCAL OUTDOOR SPORT) | Park upgrade | 2031 - 2036 | East | 0.58 | 1476000
COO-U3-003 | PCF214 | Coorparoo | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT URBAN NEIGHBOURHOOD & LOCAL OUTDOOR SPORT) | Park upgrade | 2031 - 2036 | East | 1.44 | 1476000
CVE-A1-002 | PCF333 | Calamvale | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | South | 0.8 | 3288259
CVE-E2-002 | PCF333 | Calamvale | Embellish with DISTRICT GENERAL RECREATION infrastructure | Park Embellishment | 2021 - 2026 | South | 3 | 12723028
DAR-U1-011 | PCF270 | Darra | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT OUTDOOR SPORT) | Park upgrade | 2026 - 2031 | South | 5.15 | 2829000
DAR-U3-001 | PCF270 | Darra | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION) | Park upgrade | 2031 - 2036 | South | 1 | 1476000
DEA-U2-010 | PCF53 | Deagon | Upgrade existing park infrastructure to the value of $1-2m (DISTRICT OUTDOOR SPORT) | Park upgrade | 2031 - 2036 | North | 14.55 | 2214000
DOO-A1-002 | PCF311 | Doolandella | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | South | 0.8 | 2590851
DOO-E1-001 | PCF311 | Doolandella | Embellish with LOCAL GENERAL RECREATION infrastructure | Park Embellishment | 2021 - 2026 | South | 0.5 | 763242
DUP-U2-001 | PCF212 | Dutton Park | Upgrade existing park infrastructure to the value of $1-2m (DISTRICT GENERAL RECREATION) | Park upgrade | 2026 - 2031 | South | 8.27 | 2121750
DUR-A1-002 | PCF291 | Durack | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | South | 0.7418 | 3263436
DUR-E1-001 | PCF311 | Durack | Embellish with LOCAL GENERAL RECREATION infrastructure | Park Embellishment | 2026 - 2031 | South | 0.92 | 862840
DUR-E12-001 | PCF311 | Durack | Embellish with DISTRICT NATURE RECREATION infrastructure | Park Embellishment | 2031 - 2036 | South | 6.14 | 2884957
DUR-E2-001 | PCF291 | Durack | Embellish with DISTRICT GENERAL RECREATION infrastructure | Park Embellishment | 2021 - 2026 | South | 6.4 | 13314815
EAB-U3-001 | PCF213 | East Brisbane | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT URBAN NEIGHBOURHOOD) | Park upgrade | 2026 - 2031 | East | 1.64 | 1414500
ELG-A1-001 | PCF310 | Ellen Grove | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | South | 0.6 | 1614508
ELG-A1-002 | PCF310 | Ellen Grove | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | South | 0.6 | 1768182
ELG-E12-001 | PCF310 | Ellen Grove | Embellish with LOCAL NATURE RECREATION infrastructure | Park Embellishment | 2026 - 2031 | South | 2.54 | 1314278
ELG-E2-002 | PCF310 | Ellen Grove | Embellish with DISTRICT GENERAL RECREATION infrastructure | Park Embellishment | 2021 - 2026 | South | 4.03 | 13230977
ELG-E5-001 | PCF310 | Ellen Grove | Embellish with DISTRICT OUTDOOR SPORT infrastructure | Park Embellishment | 2021 - 2026 | South | 1.44 | 13116977
EMP-U3-001 | PCF274 | Eight Mile Plains, Macgregor | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION) | Park upgrade | 2031 - 2036 | South | 0.09 | 1476000
EVP-A1-001 | PCF111 | Everton Park | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | West | 0.8 | 3648259
EVP-A1-003 | PCF111 | Everton Park | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | West | 0.61 | 11174898
EVP-U3-001 | PCF131 | Everton Park | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT GENERAL RECREATION) | Park upgrade | 2021 - 2026 | West | 12.53 | 1322250
FLK-U3-001 | PCF310 | Forest Lake | Upgrade existing park infrastructure to the value of up to $1m (LOCAL OUTDOOR SPORT) | Park upgrade | 2026 - 2031 | South | 0.3 | 1414500
FTP-E1-001 | PCF230 | Fig Tree Pocket | Embellish with LOCAL GENERAL RECREATION infrastructure | Park Embellishment | 2031 - 2036 | West | 0.5 | 851992
FTP-U3-001 | PCF250 | Fig Tree Pocket | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT GENERAL RECREATION) | Park upgrade | 2031 - 2036 | West | 7.87 | 1476000
FTZ-E5-001 | PCF73 | Fitzgibbon | Embellish with DISTRICT OUTDOOR SPORT infrastructure | Park Embellishment | 2026 - 2031 | North | 6 | 15501507
FVA-A4-001 | PCF173 | Fortitude Valley | Acquire and embellish land to provide DISTRICT URBAN COMMON infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | North | 0.3 | 13576080
FVA-U3-001 | PCF173 | Fortitude Valley | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION) | Park upgrade | 2031 - 2036 | North | 0.3 | 1476000
GAP-U2-001 | PCF149 | The Gap | Upgrade existing park infrastructure to the value of $1-2m (LOCAL OUTDOOR SPORT & DISTRICT GENERAL RECREATION) | Park upgrade | 2021 - 2026 | West | 7.04 | 1983375
GRA-A1-001 | PCF231 | Graceville | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | South | 0.2673 | 5944690
GRE-A4-001 | PCF233 | Greenslopes | Acquire and embellish land to provide DISTRICT URBAN COMMON infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | East | 0.13 | 2654523
GRE-U1-010 | PCF213 | Greenslopes | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT GENERAL RECREATION) | Park upgrade | 2031 - 2036 | East | 1 | 2952000
GUM-A7-001 | PCF217 | Gumdale | Acquire and embellish land to provide LOCAL ACCESS/ RECREATION CORRIDOR infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | East | 0.15 | 271110
HEA-A1-001 | PCF331 | Heathwood | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | South | 0.28 | 1693927
HEM-U2-001 | PCF176 | Hemmant | Upgrade existing park infrastructure to the value of $1-2m (DISTRICT GENERAL RECREATION) | Park upgrade | 2026 - 2031 | East | 5.8 | 2121750
HEN-A1-001 | PCF154 | Hendra | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | North | 1 | 1477011
HER-E3-001 | PCF172 | Herston | Embellish with METROPOLITAN GENERAL RECREATION infrastructure | Park Embellishment | 2021 - 2026 | West | 25 | 14579411
HPW-A1-001 | PCF233 | Holland Park West | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | East | 2 | 2220773
HPW-A1-002 | PCF234 | Holland Park West | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | East | 0.4713 | 9081727
HPW-A7-001 | PCF233 | Holland Park West | Acquire and embellish land to provide LOCAL ACCESS/ RECREATION CORRIDOR infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | East | 1.6 | 1395160
HPW-A7-002 | PCF233 | Holland Park West | Acquire and embellish land to provide LOCAL ACCESS/ RECREATION CORRIDOR infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | East | 0.14 | 94558
INA-U1-001 | PCF291 | Inala | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT GENERAL RECREATION) | Park upgrade | 2021 - 2026 | South | 5.31 | 2644500
IND-U2-001 | PCF230 | Indooroopilly | Upgrade existing park infrastructure to the value of $1-2m (LOCAL GENERAL RECREATION & LOCAL OUTDOOR SPORT) | Park upgrade | 2026 - 2031 | West | 6 | 2121750
IND-U3-002 | PCF211 | Indooroopilly | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT URBAN NEIGHBOURHOOD) | Park upgrade | 2021 - 2026 | West | 0.93 | 1322250
IND-U3-003 | PCF210 | Indooroopilly | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION & LOCAL OUTDOOR SPORT) | Park upgrade | 2031 - 2036 | West | 1.57 | 1476000
IND-U3-004 | PCF231 | Indooroopilly | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION) | Park upgrade | 2031 - 2036 | West | 0.5 | 1476000
IND-U3-005 | PCF211 | Indooroopilly | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION & LOCAL OUTDOOR SPORT) | Park upgrade | 2031 - 2036 | West | 0.99 | 1476000
KAD-E1-001 | PCF245 | Karana Downs | Embellish with LOCAL GENERAL RECREATION infrastructure | Park Embellishment | 2031 - 2036 | West | 1.96 | 1020110
KAN-A8-001 | PCF193 | Kangaroo Point | Acquire and embellish land to provide METROPOLITAN ACCESS/ RECREATION CORRIDOR infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | East | 0.01 | 1555740
KAN-A8-002 | PCF193 | Kangaroo Point | Acquire and embellish land to provide METROPOLITAN ACCESS/ RECREATION CORRIDOR infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | East | 0.01 | 1555740
KAN-A8-003 | PCF193 | Kangaroo Point | Acquire and embellish land to provide METROPOLITAN ACCESS/ RECREATION CORRIDOR infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | East | 0.01 | 1555740
KAN-U1-001 | PCF193 | Kangaroo Point | Upgrade existing park infrastructure to the value of $2m+ (METROPOLITAN GENERAL RECREATION) | Park upgrade | 2026 - 2031 | East | 10.8 | 2829000
KAN-U2-001 | PCF193 | Kangaroo Point | Upgrade existing park infrastructure to the value of $1-2m (DISTRICT OUTDOOR SPORT) | Park upgrade | 2026 - 2031 | East | 1.9 | 2121750
KED-A1-001 | PCF132 | Kedron | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | West | 0.5644 | 9144267
KED-U1-010 | PCF112 | Kedron | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT GENERAL RECREATION) | Park upgrade | 2021 - 2026 | West | 2.9 | 2644500
KEN-U3-001 | PCF230 | Kenmore | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION) | Park upgrade | 2031 - 2036 | West | 0.44 | 1476000
KEN-U3-002 | PCF229 | Kenmore | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION) | Park upgrade | 2026 - 2031 | West | 0.8 | 1414500
KGR-U3-001 | PCF172 | Kelvin Grove | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT URBAN NEIGHBOURHOOD) | Park upgrade | 2031 - 2036 | West | 1.4 | 1476000
KHO-E11-001 | PCF203 | Kholo | Embellish with DISTRICT VISITOR NODE infrastructure | Park Embellishment | 2021 - 2026 | West | 19.99 | 13672512
KHO-E11-002 | PCF225 | Kholo | Embellish with DISTRICT VISITOR NODE infrastructure | Park Embellishment | 2031 - 2036 | West | 3.4 | 5833332
KNH-U3-001 | PCF209 | Kenmore Hills | Upgrade existing park infrastructure to the value of up to $1m (LOCAL OUTDOOR SPORT & LOCAL GENERAL RECREATION) | Park upgrade | 2031 - 2036 | West | 4 | 1476000
KRR-E11-001 | PCF129 | Upper Kedron | Embellish with DISTRICT VISITOR NODE infrastructure | Park Embellishment | 2026 - 2031 | West | 2 | 4827736
KRR-E12-001 | PCF149 | Keperra | Embellish with DISTRICT NATURE RECREATION infrastructure | Park Embellishment | 2026 - 2031 | West | 15.326 | 2764751
KUR-U3-001 | PCF314 | Kuraby | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION) | Park upgrade | 2031 - 2036 | South | 0.82 | 1476000
KWA-E12-001 | PCF354 | Karawatha | Embellish with DISTRICT NATURE RECREATION infrastructure | Park Embellishment | 2031 - 2036 | South | 5.55 | 2768789
KWA-E5-001 | PCF354 | Karawatha | Embellish with DISTRICT OUTDOOR SPORT infrastructure | Park Embellishment | 2031 - 2036 | South | 2.86 | 15119675
KWA-U1-001 | PCF334 | Karawatha | Upgrade existing park infrastructure to the value of $2m+ (METROPOLITAN NATURE RECREATION & DISTRICT VISITOR NODE) | Park upgrade | 2031 - 2036 | South | 14.75 | 2952000
LPA-E12-001 | PCF352 | Larapinta | Embellish with DISTRICT NATURE RECREATION infrastructure | Park Embellishment | 2021 - 2026 | South | 12.429 | 2584441
LUT-E1-004 | PCF153 | Lutwyche | Embellish with LOCAL GENERAL RECREATION infrastructure | Park Embellishment | 2021 - 2026 | North | 0.69 | 782842
MCG-E1-001 | PCF274 | Macgregor | Embellish with LOCAL GENERAL RECREATION infrastructure | Park Embellishment | 2031 - 2036 | South | 0.2 | 817447
MCG-E1-002 | PCF274 | Macgregor | Embellish with LOCAL GENERAL RECREATION infrastructure | Park Embellishment | 2021 - 2026 | South | 0.54 | 767369
MCG-U3-001 | PCF274 | Macgregor | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT GENERAL RECREATION) | Park upgrade | 2021 - 2026 | South | 4.41 | 1322250
MCO-U1-001 | PCF189 | Mount Coot-Tha | Upgrade existing park infrastructure to the value of $2m+ (METROPOLITAN VISITOR NODE & METROPOLITAN NATURE RECREATION) | Park upgrade | 2026 - 2031 | West | 28.32 | 2829000
MCO-U1-011 | PCF191 | Mount Coot-Tha | Upgrade existing park infrastructure to the value of $2m+ (METROPOLITAN BOTANIC GARDEN/ ARBORETUM) | Park upgrade | 2021 - 2026 | West | 44.83 | 2644500
MCR-E11-001 | PCF245 | Mount Crosby | Embellish with DISTRICT VISITOR NODE infrastructure | Park Embellishment | 2031 - 2036 | West | 2 | 5037637
MDW-A1-001 | PCF111 | Mcdowall | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | West | 0.5 | 1916006
MFI-A1-001 | PCF255 | Mansfield | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | East | 0.5622 | 9142789
MGR-A1-001 | PCF254 | Mount Gravatt | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | East | 0.5444 | 9083714
MGR-U2-001 | PCF254 | Mount Gravatt | Upgrade existing park infrastructure to the value of $1-2m (METROPOLITAN VISITOR NODE) | Park upgrade | 2021 - 2026 | East | 1.56 | 1983375
MIL-U2-001 | PCF192 | Milton | Upgrade existing park infrastructure to the value of $1-2m (DISTRICT URBAN COMMON) | Park upgrade | 2026 - 2031 | West | 0.15 | 2121750
MIL-U3-001 | PCF191 | Milton | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT URBAN NEIGHBOURHOOD & LOCAL OUTDOOR SPORT) | Park upgrade | 2031 - 2036 | West | 2.09 | 1476000
MIT-A1-001 | PCF130 | Mitchelton | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | West | 0.8 | 3702532
MIT-A4-001 | PCF131 | Mitchelton | Acquire and embellish land to provide DISTRICT URBAN COMMON infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | West | 0.32 | 7983259
MKA-A1-001 | PCF232 | Moorooka | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | South | 0.5827 | 11108370
MNW-A7-002 | PCF177 | Manly West | Acquire and embellish land to provide LOCAL ACCESS/ RECREATION CORRIDOR infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | East | 0.2 | 104009
MNW-A7-003 | PCF197, PCF196 | Manly West | Acquire and embellish land to provide LOCAL ACCESS/ RECREATION CORRIDOR infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | East | 0.3 | 139973
MNW-E7-001 | PCF177 | Manly West | Embellish with LOCAL ACCESS/ RECREATION CORRIDOR infrastructure | Park Embellishment | 2031 - 2036 | East | 2.7 | 1884281
MOG-A1-004 | PCF268 | Moggill | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | West | 0.5 | 1555131
MOG-E2-001 | PCF288 | Moggill | Embellish with DISTRICT GENERAL RECREATION infrastructure | Park Embellishment | 2026 - 2031 | West | 8.2 | 14243755
MOG-U3-001 | PCF268 | Moggill | Upgrade existing park infrastructure to the value of up to $1m (LOCAL VISITOR NODE) | Park upgrade | 2031 - 2036 | West | 4.34 | 1476000
MUR-U1-011 | PCF175 | Murarrie | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT GENERAL RECREATION) | Park upgrade | 2021 - 2026 | East | 8.99 | 2644500
MUR-U1-012 | PCF195 | Murarrie | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT GENERAL RECREATION) | Park upgrade | 2026 - 2031 | East | 10.03 | 2829000
MUR-U1-013 | PCF195 | Murarrie | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT OUTDOOR SPORT) | Park upgrade | 2021 - 2026 | East | 18.84 | 2644500
NAN-U2-001 | PCF253 | Nathan | Upgrade existing park infrastructure to the value of $1-2m (METROPOLITAN NATURE RECREATION) | Park upgrade | 2026 - 2031 | South | 19.259 | 2121750
NBE-U3-001 | PCF75 | Nudgee Beach | Upgrade existing park infrastructure to the value of $1-2m (LOCAL OUTDOOR SPORT & DISTRICT GENERAL RECREATION) | Park upgrade | 2031 - 2036 | North | 6.53 | 1476000
NRP-U3-001 | PCF193 | Norman Park | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT URBAN NEIGHBOURHOOD) | Park upgrade | 2026 - 2031 | East | 1.43 | 1414500
NUD-E5-001 | PCF94 | Nudgee | Embellish with DISTRICT OUTDOOR SPORT infrastructure | Park Embellishment | 2021 - 2026 | North | 6.31 | 14583918
NUD-U3-010 | PCF95 | Nudgee | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT GENERAL RECREATION) | Park upgrade | 2021 - 2026 | North | 2.71 | 1322250
NWM-U1-001 | PCF152 | Wilston | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT OUTDOOR SPORT & DISTRICT GENERAL RECREATION) | Park upgrade | 2026 - 2031 | West | 25.93 | 2829000
NWS-U2-001 | PCF173 | Newstead | Upgrade existing park infrastructure to the value of $1-2m (DISTRICT OUTDOOR SPORT) | Park upgrade | 2026 - 2031 | North | 0.51 | 2121750
PAD-U3-001 | PCF172 | Paddington | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT URBAN NEIGHBOURHOOD & LOCAL OUTDOOR SPORT) | Park upgrade | 2031 - 2036 | West | 1.31 | 1476000
PAL-A1-001 | PCF332 | Pallara | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | South | 0.8 | 1246851
PAL-A1-002 | PCF312 | Pallara | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | South | 0.8 | 1246851
PAL-A2-001 | PCF312 | Pallara | Acquire and embellish land to provide DISTRICT GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | South | 3.2 | 17129291
PAL-A5-001 | PCF331 | Pallara | Acquire and embellish land to provide DISTRICT OUTDOOR SPORT (& LOCAL GENERAL RECREATION) infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | South | 4.9 | 20598944
PAL-A7-001 | PCF312 | Pallara | Acquire and embellish land to provide LOCAL ACCESS/ RECREATION CORRIDOR infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | South | 1.7 | 1461680
PAR-A1-001 | PCF333 | Parkinson | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | South | 0.6 | 2919508
PAR-U3-001 | PCF332 | Parkinson | Upgrade existing park infrastructure to the value of up to $1m (LOCAL OUTDOOR SPORT & DISTRICT GENERAL RECREATION) | Park upgrade | 2031 - 2036 | South | 4.19 | 1476000
RIC-A1-005 | PCF290 | Richlands | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | South | 0.2 | 1399480
RIC-E1-001 | PCF290 | Richlands | Embellish with LOCAL GENERAL RECREATION infrastructure | Park Embellishment | 2026 - 2031 | South | 2.35 | 1020643
RIC-E5-001 | PCF290 | Richlands | Embellish with DISTRICT OUTDOOR SPORT infrastructure | Park Embellishment | 2021 - 2026 | South | 5.42 | 14315832
RIC-U3-001 | PCF290 | Richlands | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION) | Park upgrade | 2021 - 2026 | South | 0.96 | 1322250
ROB-A1-001 | PCF273 | Robertson | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | South | 0.7 | 5435356
ROC-A1-002 | PCF295 | Rochedale | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | East | 0.6 | 2745508
ROC-A1-003 | PCF295 | Rochedale | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | East | 0.25 | 1585874
ROC-A1-010 | PCF276 | Rochedale | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | East | 0.8 | 3648259
ROC-A1-011 | PCF276 | Rochedale | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | East | 0.5 | 2410131
ROC-A1-012 | PCF276 | Rochedale | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | East | 0.8 | 3532259
ROC-A1-013 | PCF276 | Rochedale | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | East | 0.8 | 3470532
ROC-A1-014 | PCF276 | Rochedale | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | East | 0.8 | 3470532
ROC-A1-015 | PCF276 | Rochedale | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | East | 0.5 | 2341318
ROC-A1-018 | PCF276, PCF296 | Rochedale | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | East | 0.8 | 3702532
ROC-A1-019 | PCF295 | Rochedale | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | East | 0.8 | 2870851
ROC-A1-020 | PCF295 | Rochedale | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | East | 0.5 | 2482631
ROC-A1-023 | PCF295 | Rochedale | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | East | 0.55 | 1189594
ROC-A1-030 | PCF275 | Rochedale | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | East | 0.6 | 2919508
ROC-A1-031 | PCF275 | Rochedale | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | East | 0.8 | 3184259
ROC-A1-032 | PCF295 | Rochedale | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | East | 0.59 | 2540870
ROC-A2-010 | PCF295 | Rochedale | Acquire and embellish land to provide DISTRICT GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | East | 1.7 | 15709763
ROC-A2-011 | PCF276 | Rochedale | Acquire and embellish land to provide DISTRICT GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | East | 3 | 21265502
ROC-A5-001 | PCF276 | Rochedale | Acquire and embellish land to provide DISTRICT OUTDOOR SPORT infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | East | 6.8 | 37250176
ROC-E1-001 | PCF275 | Rochedale | Embellish with LOCAL GENERAL RECREATION infrastructure | Park Embellishment | 2021 - 2026 | East | 1.11 | 826167
ROC-E5-002 | PCF296 | Rochedale | Embellish with METROPOLITAN OUTDOOR SPORT infrastructure | Park Embellishment | 2026 - 2031 | East | 14.37 | 24676456
ROK-E3-001 | PCF251 | Rocklea | Embellish with METROPOLITAN GENERAL RECREATION infrastructure | Park Embellishment | 2026 - 2031 | South | 120.4 | 15596579
RUN-A1-001 | PCF314 | Runcorn | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | South | 0.36 | 938069
RUN-A1-003 | PCF294 | Runcorn | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | South | 3 | 7314536
RUN-E5-001 | PCF295 | Runcorn | Embellish with DISTRICT OUTDOOR SPORT infrastructure | Park Embellishment | 2021 - 2026 | South | 5.21 | 14252575
RUN-U3-001 | PCF294 | Runcorn | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT OUTDOOR SPORT & DISTRICT GENERAL RECREATION) | Park upgrade | 2031 - 2036 | South | 3.98 | 1476000
RUN-U3-002 | PCF314 | Runcorn | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT GENERAL RECREATION & LOCAL OUTDOOR SPORT) | Park upgrade | 2026 - 2031 | South | 3 | 1414500
SAL-A1-001 | PCF252 | Salisbury | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | South | 0.6219 | 5182893
SBR-A1-001 | PCF192 | South Brisbane | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | South | 1 | 23436881
SBR-A1-002 | PCF212 | South Brisbane | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | South | 0.228 | 7880028
SBR-A2-001 | PCF192 | South Brisbane | Acquire and embellish land to provide DISTRICT GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | South | 1 | 33147741
SBR-U1-010 | PCF192 | South Brisbane | Upgrade existing park infrastructure to the value of $2m+ (METROPOLITAN ACCESS/ RECREATION CORRIDOR) | Park upgrade | 2026 - 2031 | South | 2.32 | 2829000
SBR-U2-001 | PCF192 | South Brisbane | Upgrade existing park infrastructure to the value of $1-2m (METROPOLITAN GENERAL RECREATION) | Park upgrade | 2021 - 2026 | South | 5 | 1983375
SHI-A4-001 | PCF172 | Spring Hill | Acquire and embellish land to provide DISTRICT URBAN COMMON infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | West | 0.182 | 8743716
SHI-U1-001 | PCF172 | Spring Hill | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT OUTDOOR SPORT) | Park upgrade | 2026 - 2031 | West | 4 | 2829000
SHI-U3-001 | PCF172 | Spring Hill | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT URBAN NEIGHBOURHOOD & LOCAL OUTDOOR SPORT) | Park upgrade | 2026 - 2031 | West | 1.17 | 1414500
SHI-U3-002 | PCF172 | Spring Hill | Upgrade existing park infrastructure to the value of up to $1m (METROPOLITAN GENERAL RECREATION) | Park upgrade | 2031 - 2036 | West | 0.15 | 1476000
SLU-U3-001 | PCF211 | St Lucia | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT URBAN NEIGHBOURHOOD) | Park upgrade | 2031 - 2036 | West | 0.69 | 1476000
SLU-U3-002 | PCF212 | St Lucia | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION) | Park upgrade | 2031 - 2036 | West | 0.2 | 1476000
SMN-U3-010 | PCF269 | Sumner | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT OUTDOOR SPORT) | Park upgrade | 2031 - 2036 | South | 4.31 | 1476000
SNH-E1-001 | PCF293 | Sunnybank Hills | Embellish with LOCAL GENERAL RECREATION infrastructure | Park Embellishment | 2031 - 2036 | South | 0.4 | 840478
STC-U1-001 | PCF213 | Stones Corner | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT GENERAL RECREATION) | Park upgrade | 2021 - 2026 | East | 5.04 | 2644500
STF-U1-011 | PCF132 | Stafford | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT GENERAL RECREATION) | Park upgrade | 2021 - 2026 | West | 2.79 | 2644500
STN-A5-001 | PCF314 | Stretton | Acquire and embellish land to provide DISTRICT OUTDOOR SPORT infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | South | 2.4216 | 26567936
SUN-A1-001 | PCF273 | Sunnybank | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | South | 0.5 | 2851006
SVH-E12-001 | PCF194 | Seven Hills | Embellish with DISTRICT NATURE RECREATION infrastructure | Park Embellishment | 2031 - 2036 | East | 5.828 | 2840555
SWD-U2-001 | PCF231 | Sherwood | Upgrade existing park infrastructure to the value of $1-2m (DISTRICT BOTANIC GARDEN/ ARBORETUM) | Park upgrade | 2021 - 2026 | South | 15.84 | 1983375
TAI-A1-001 | PCF73 | Taigum | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | North | 0.5 | 2601006
TAI-E1-002 | PCF73 | Taigum | Embellish with LOCAL GENERAL RECREATION infrastructure | Park Embellishment | 2026 - 2031 | North | 1.6 | 937880
TAR-A1-001 | PCF211 | Taringa | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | West | 0.07 | 778313
TAR-U1-001 | PCF211 | Taringa | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT URBAN NEIGHBOURHOOD & LOCAL OUTDOOR SPORT) | Park upgrade | 2021 - 2026 | West | 1.06 | 2644500
TAR-U3-010 | PCF211 | Taringa | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION) | Park upgrade | 2021 - 2026 | West | 2.46 | 1322250
TOO-A4-002 | PCF191 | Toowong | Acquire and embellish land to provide DISTRICT URBAN COMMON infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | West | 0.1257 | 7302753
TOO-U3-001 | PCF191 | Toowong | Upgrade existing park infrastructure to the value of up to $1m (LOCAL OUTDOOR SPORT) | Park upgrade | 2031 - 2036 | West | 0.5 | 1476000
TRF-A8-001 | PCF173 | Teneriffe | Acquire and embellish land to provide METROPOLITAN ACCESS/ RECREATION CORRIDOR infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | North | 0.13 | 4779778
UKE-A1-005 | PCF149 | Upper Kedron | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | West | 0.5 | 1351006
UKE-E5-001 | PCF129 | Upper Kedron | Embellish with DISTRICT OUTDOOR SPORT infrastructure | Park Embellishment | 2026 - 2031 | West | 4.5 | 15018154
UMG-E4-001 | PCF274 | Upper Mount Gravatt | Embellish with DISTRICT URBAN COMMON infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | East | 0.28 | 3683389
UMG-U3-001 | PCF254 | Upper Mount Gravatt | Upgrade existing park infrastructure to the value of up to $1m (LOCAL OUTDOOR SPORT & DISTRICT GENERAL RECREATION) | Park upgrade | 2031 - 2036 | East | 1.78 | 1476000
WAK-A7-001 | PCF196 | Wakerley | Acquire and embellish land to provide LOCAL ACCESS/ RECREATION CORRIDOR infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | East | 0.06 | 163504
WAK-U3-001 | PCF197 | Wakerley | Upgrade existing park infrastructure to the value of up to $1m (LOCAL OUTDOOR SPORT & DISTRICT GENERAL RECREATION) | Park upgrade | 2031 - 2036 | East | 4.61 | 1476000
WES-A1-002 | PCF192 | West End | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | South | 0.46 | 15962248
WES-A7-001 | PCF192 | West End | Acquire and embellish land to provide LOCAL ACCESS/ RECREATION CORRIDOR infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | South | 0.05 | 1162246
WES-U1-010 | PCF192 | West End | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT GENERAL RECREATION & DISTRICT OUTDOOR SPORT) | Park upgrade | 2021 - 2026 | South | 5.75 | 2644500
WES-U1-012 | PCF211 | West End | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT GENERAL RECREATION) | Park upgrade | 2021 - 2026 | South | 2.02 | 2644500
WIL-E1-001 | PCF312 | Willawong | Embellish with LOCAL GENERAL RECREATION infrastructure | Park Embellishment | 2026 - 2031 | South | 0.46 | 812078
WIL-U3-010 | PCF291 | Willawong | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT OUTDOOR SPORT) | Park upgrade | 2026 - 2031 | South | 11.75 | 1414500
WOO-A4-001 | PCF213 | Woolloongabba | Acquire and embellish land to provide DISTRICT URBAN COMMON infrastructure | Park acquisition and embellishment - specific location | 2031 - 2036 | South | 0.06 | 2350918
WSR-E1-001 | PCF152 | Windsor | Embellish with LOCAL GENERAL RECREATION infrastructure | Park Embellishment | 2021 - 2026 | West | 1.24 | 839577
WSR-U1-001 | PCF152 | Windsor | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT OUTDOOR SPORT & DISTRICT GENERAL RECREATION) | Park upgrade | 2026 - 2031 | West | 25.7 | 2829000
WSR-U3-001 | PCF153 | Windsor | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT GENERAL RECREATION) | Park upgrade | 2026 - 2031 | North | 4.12 | 1414500
WSR-U3-010 | PCF153 | Windsor | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION) | Park upgrade | 2021 - 2026 | North | 1 | 1322250
WVH-U3-010 | PCF133 | Wavell Heights | Upgrade existing park infrastructure to the value of up to $1m (DISTRICT GENERAL RECREATION) | Park upgrade | 2021 - 2026 | North | 2 | 1322250
WWN-A1-001 | PCF153 | Wooloowin | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2026 - 2031 | North | 0.5 | 6680131
WYN-U1-010 | PCF157 | Wynnum | Upgrade existing park infrastructure to the value of $2m+ (DISTRICT OUTDOOR SPORT) | Park upgrade | 2021 - 2026 | East | 12.16 | 2644500
WYN-U3-010 | PCF177 | Wynnum | Upgrade existing park infrastructure to the value of up to $1m (LOCAL GENERAL RECREATION) | Park upgrade | 2021 - 2026 | East | 0.5 | 1322250
WYW-A1-001 | PCF177 | Wynnum West | Acquire and embellish land to provide LOCAL GENERAL RECREATION infrastructure | Park acquisition and embellishment - specific location | 2021 - 2026 | East | 0.38 | 2282105
ZIL-U1-010 | PCF93 | Zillmere | Upgrade existing park infrastructure to the value of $2m+ (METROPOLITAN OUTDOOR SPORT) | Park upgrade | 2026 - 2031 | North | 28.6 | 2829000
[7 empty] | Total | 1061000281
Notes-
(1) Refer to the Local government infrastructure plan identifier (LGIP ID) when identifying the infrastructure projects on the plans for trunk infrastructure maps.
(2) The estimated year of completion is an estimate of the earliest need for the project.
(3) Establishment cost is the total value of the trunk infrastructure item, at 30 June 2021.
(-) A dash denotes that the field is not applicable.

## Sheet2
Column1 | Column2
ACR-U1-001 | 2829000
AGR-A1-002 | 998002
AGR-A1-003 | 1508356
AGR-U3-001 | 1476000
ALB-A1-002 | 1842661
ALD-U1-001 | 2644500
ALD-U3-001 | 1414500
ANS-U3-001 | 1322250
ASC-A1-002 | 2185131
ASC-A1-003 | 6587206
ASP-A1-001 | 9103694
ASP-A8-002 | 157436
AUC-U3-001 | 1476000
BDL-U3-001 | 1414500
BFD-E11-001 | 4469281
BFD-E12-001 | 3933844
BHI-E12-001 | 2764751
BNE-U1-001 | 2829000
BRD-A1-003 | 2248259
BRD-A1-004 | 3566851
BRD-A1-005 | 1533831
BRD-A2-001 | 20141076
BRD-U2-001 | 1983375
BRD-U2-002 | 2214000
BRD-U3-001 | 1322250
BRD-U3-002 | 1414500
BRG-A1-001 | 1241785
BRI-U3-001 | 1414500
BUL-A1-001 | 13248259
BUL-A8-001 | 4104632
BUL-A8-010 | 28214146
BUR-E11-001 | 4469281
BUR-E12-001 | 2884957
BUR-U3-001 | 1414500
BUR-U3-002 | 1414500
BWE-U3-001 | 1322250
BYO-A1-001 | 3648259
CAH-U3-001 | 1322250
CAR-A1-001 | 1036318
CAR-A1-002 | 9091334
CDE-U3-001 | 1476000
CDE-U3-010 | 1322250
CHE-E1-001 | 883082
CHE-U2-002 | 2214000
CHE-U3-001 | 1476000
CHE-U3-002 | 1414500
CHL-U2-001 | 1983375
CHL-U3-001 | 1414500
CHW-U3-001 | 1476000
CLF-A1-001 | 2899590
CLF-A1-002 | 6873526
CLL-A1-001 | 2956691
CLL-A1-010 | 2981714
COO-U3-001 | 1322250
COO-U3-002 | 1476000
COO-U3-003 | 1476000
CVE-A1-002 | 3288259
CVE-E2-002 | 12723028
DAR-U1-011 | 2829000
DAR-U3-001 | 1476000
DEA-U2-010 | 2214000
DOO-A1-002 | 2590851
DOO-E1-001 | 763242
DUP-U2-001 | 2121750
DUR-A1-002 | 3263436
DUR-E1-001 | 862840
DUR-E12-001 | 2884957
DUR-E2-001 | 13314815
EAB-U3-001 | 1414500
ELG-A1-001 | 1614508
ELG-A1-002 | 1768182
ELG-E12-001 | 1314278
ELG-E2-002 | 13230977
ELG-E5-001 | 13116977
EMP-U3-001 | 1476000
EVP-A1-001 | 3648259
EVP-A1-003 | 11174898
EVP-U3-001 | 1322250
FLK-U3-001 | 1414500
FTP-E1-001 | 851992
FTP-U3-001 | 1476000
FTZ-E5-001 | 15501507
FVA-A4-001 | 13576080
FVA-U3-001 | 1476000
GAP-U2-001 | 1983375
GRA-A1-001 | 5944690
GRE-A4-001 | 2654523
GRE-U1-010 | 2952000
GUM-A7-001 | 271110
HEA-A1-001 | 1693927
HEM-U2-001 | 2121750
HEN-A1-001 | 1477011
HER-E3-001 | 14579411
HPW-A1-001 | 2220773
HPW-A1-002 | 9081727
HPW-A7-001 | 1395160
HPW-A7-002 | 94558
INA-U1-001 | 2644500
IND-U2-001 | 2121750
IND-U3-002 | 1322250
IND-U3-003 | 1476000
IND-U3-004 | 1476000
IND-U3-005 | 1476000
KAD-E1-001 | 1020110
KAN-A8-001 | 1555740
KAN-A8-002 | 1555740
KAN-A8-003 | 1555740
KAN-U1-001 | 2829000
KAN-U2-001 | 2121750
KED-A1-001 | 9144267
KED-U1-010 | 2644500
KEN-U3-001 | 1476000
KEN-U3-002 | 1414500
KGR-U3-001 | 1476000
KHO-E11-001 | 13672512
KHO-E11-002 | 5833332
KNH-U3-001 | 1476000
KRR-E11-001 | 4827736
KRR-E12-001 | 2764751
KUR-U3-001 | 1476000
KWA-E12-001 | 2768789
KWA-E5-001 | 15119675
KWA-U1-001 | 2952000
LPA-E12-001 | 2584441
LUT-E1-004 | 782842
MCG-E1-001 | 817447
MCG-E1-002 | 767369
MCG-U3-001 | 1322250
MCO-U1-001 | 2829000
MCO-U1-011 | 2644500
MCR-E11-001 | 5037637
MDW-A1-001 | 1916006
MFI-A1-001 | 9142789
MGR-A1-001 | 9083714
MGR-U2-001 | 1983375
MIL-U2-001 | 2121750
MIL-U3-001 | 1476000
MIT-A1-001 | 3702532
MIT-A4-001 | 7983259
MKA-A1-001 | 11108370
MNW-A7-002 | 104009
MNW-A7-003 | 139973
MNW-E7-001 | 1884281
MOG-A1-004 | 1555131
MOG-E2-001 | 14243755
MOG-U3-001 | 1476000
MUR-U1-011 | 2644500
MUR-U1-012 | 2829000
MUR-U1-013 | 2644500
NAN-U2-001 | 2121750
NBE-U3-001 | 1476000
NRP-U3-001 | 1414500
NUD-E5-001 | 14583918
NUD-U3-010 | 1322250
NWM-U1-001 | 2829000
NWS-U2-001 | 2121750
PAD-U3-001 | 1476000
PAL-A1-001 | 1246851
PAL-A1-002 | 1246851
PAL-A2-001 | 17129291
PAL-A5-001 | 20598944
PAL-A7-001 | 1461680
PAR-A1-001 | 2919508
PAR-U3-001 | 1476000
RIC-A1-005 | 1399480
RIC-E1-001 | 1020643
RIC-E5-001 | 14315832
RIC-U3-001 | 1322250
ROB-A1-001 | 5435356
ROC-A1-002 | 2745508
ROC-A1-003 | 1585874
ROC-A1-010 | 3648259
ROC-A1-011 | 2410131
ROC-A1-012 | 3532259
ROC-A1-013 | 3470532
ROC-A1-014 | 3470532
ROC-A1-015 | 2341318
ROC-A1-018 | 3702532
ROC-A1-019 | 2870851
ROC-A1-020 | 2482631
ROC-A1-023 | 1189594
ROC-A1-030 | 2919508
ROC-A1-031 | 3184259
ROC-A1-032 | 2540870
ROC-A2-010 | 15709763
ROC-A2-011 | 21265502
ROC-A5-001 | 37250176
ROC-E1-001 | 826167
ROC-E5-002 | 24676456
ROK-E3-001 | 15596579
RUN-A1-001 | 938069
RUN-A1-003 | 7314536
RUN-E5-001 | 14252575
RUN-U3-001 | 1476000
RUN-U3-002 | 1414500
SAL-A1-001 | 5182893
SBR-A1-001 | 23436881
SBR-A1-002 | 7880028
SBR-A2-001 | 33147741
SBR-U1-010 | 2829000
SBR-U2-001 | 1983375
SHI-A4-001 | 8743716
SHI-U1-001 | 2829000
SHI-U3-001 | 1414500
SHI-U3-002 | 1476000
SLU-U3-001 | 1476000
SLU-U3-002 | 1476000
SMN-U3-010 | 1476000
SNH-E1-001 | 840478
STC-U1-001 | 2644500
STF-U1-011 | 2644500
STN-A5-001 | 26567936
SUN-A1-001 | 2851006
SVH-E12-001 | 2840555
SWD-U2-001 | 1983375
TAI-A1-001 | 2601006
TAI-E1-002 | 937880
TAR-A1-001 | 778313
TAR-U1-001 | 2644500
TAR-U3-010 | 1322250
TOO-A4-002 | 7302753
TOO-U3-001 | 1476000
TRF-A8-001 | 4779778
UKE-A1-005 | 1351006
UKE-E5-001 | 15018154
UMG-E4-001 | 3683389
UMG-U3-001 | 1476000
WAK-A7-001 | 163504
WAK-U3-001 | 1476000
WES-A1-002 | 15962248
WES-A7-001 | 1162246
WES-U1-010 | 2644500
WES-U1-012 | 2644500
WIL-E1-001 | 812078
WIL-U3-010 | 1414500
WOO-A4-001 | 2350918
WSR-E1-001 | 839577
WSR-U1-001 | 2829000
WSR-U3-001 | 1414500
WSR-U3-010 | 1322250
WVH-U3-010 | 1322250
WWN-A1-001 | 6680131
WYN-U1-010 | 2644500
WYN-U3-010 | 1322250
WYW-A1-001 | 2282105
ZIL-U1-010 | 2829000
1061000281