## Slide 1: Kelvin Grove Road and Enoggera Road Traffic Improvements
Infrastructure Committee
29 November 2022

## Slide 2: Locations
Source: BrisMap
Enoggera Rd
Moran St
Kelvin Grove Rd
Blamey St

## Slide 3: Kelvin Grove Road and Blamey Street - Project plan
Source: Council
Source: Council

## Slide 4: Kelvin Grove Road and Blamey Street - Details
Background
  The intersection is at capacity, particularly in the afternoon peak travel period
Objectives
  Improve safety for people walking and riding through the area
  Improve overall intersection traffic flow capacity by improving the right turn capacity into Blamey Street
Construction challenges
  Work in close proximity to heritage protected vegetation
  Presence of rock in excavations

## Slide 5: Enoggera Road and Moran Street - Project plan
Source: Council

## Slide 6: Enoggera Road and Moran Street - Details
Background
  The intersection has a high crash rate
  Access is difficult in and out of Moran Street
Objectives
  Improve access in and out of Moran Street
  Improve the intersection safety
  Improve active transport with formalised crossings
Construction challenges
  Extremely congested with Public Utility Plant
  Exclusively carried out at night due to high traffic volumes

## Slide 7: Delivery and funding
The completed upgrades will improve accessibility and safety
Design completed early 2022
Contracts awarded mid 2022
Construction commenced mid 2022
Enoggera Moran completed on 8 November 2022
Kelvin Blamey to be completed in December 2022
The Kelvin Grove Road and Blamey Street and Enoggera Road and Moran Street intersection upgrade projects are jointly funded by Council and the Australian Government’s Roads to Recovery Program.
Late 2021 Planning and investigation works complete
Early 2022
Detailed design and community engagement
Mid 2022
Start of Construction
Late 2022
End of construction

## Slide 8: Construction works
Source: Council
Source: Council
Stormwater installation
Blamey Street October 2022
Mast arm erection
Enoggera Road October 2022

## Slide 9: Construction works
Source: Council
Cr Wines turning the traffic signals on at Enoggera Road/Moran Street
night of 8 November 2022

## Slide 10: Overview of works
Source: Council

## Slide 11: Questions
Source: Council