## Slide 1: Retrofit Full Driver Barriers to Transport for Brisbane Fleet Transport Committee 16 May 2023

## Slide 2: State Government Funding Announcement
25 January 2023 Queensland Government announced “almost $4 million will be invested in rolling out more full bus driver barriers across the public transport network”
  $2.6M of this funding is allocated to Council buses
  Installation of approximately 150-180 safety barriers
Initial focus is Willawong Depot
  Routes 100 & 110
  Priority MAN A69 CNG Buses

## Slide 3: Full Driver Barrier Design Considerations
Challenges
Existing door and cabin design
Ticketing and cash tray
Vehicle vibration
Location of existing mirrors and cameras
Australian Design Rule approvals
Need for immediate action
Previous poor market response
Opportunities
Agreement with employees on design performance
  Prevent physical assault while the bus operator is seated
Based on successfully trialled barrier in new electric bus fleet
  Two piece toughened safety glass
  Semi-frameless design
  Smart vision Rear View Camera
    Reduces the impact of reflection in the barrier
    Enhances vision and safety
  Emergency Exit modification for driver

## Slide 4: Comparing New v Retrofit Fleet
New fleet
Retrofit fleet

## Slide 5: Smart Vision Indirect Rear View Camera
Issue identified was reflections off the barrier glass in certain situations particularly the vision to the nearside rear vision mirror
Trialled anti-reflective film was unsuccessful

## Slide 6: Consultation Process
Consistent
Collaborative
Expedite agreement for deployment
3 x Bus Design & Security Committee and Workplace Health and Safety Representative Consultation sessions
  3 Feb 23, 21 Feb 23, 12 Apr 23 & 14 Apr 23
5 weeks in service trial at Willawong – 17 Apr – 21 May 2023
Bus operator survey between 1 -21 May 2023
12 issues raised and resolved

## Slide 7: Design Process
Design completed
Prototype Full Barrier installed in Buses 1400 & 1500
ADR 14/02 confirmed
Emergency window test complete
Impact/strength testing complete
Anti-shatter testing complete
Occupational Therapist review
Stakeholder engagement

## Slide 8: Design Variations
Offside display height - Bus 1400 low, Bus 1500 high
Anti-shatter film – fitted to Bus 1500 only - confirm visibility

## Slide 9: Door Access Guard
Prevents attack through door access hole

## Slide 10: Other Key Bus Modifications
Door latch
Removal of cash tray
Single ticket validator at the front door
Relocating key equipment
Reinforcement of barn door and front dash area

## Slide 11: Smart Vision Indirect Rear View Camera Improvements
Improved wider angle vision
Safe lane clearance markers
Improved visibility at night and rain

## Slide 12: Retrofit Barrier Key Facts
Barrier design process completed by TfB internal technical staff
A total of 23 vehicle modifications are required to fit the barrier
A total of 136 unique parts
A total of 309 parts to complete the install
Installation expected to take 2.5 to 3 days per bus

## Slide 13: Next Steps
Complete consultation
Sign contracts for delivery of glass and smart vision rear view cameras
Confirm agreement with Translink.
Lead time for parts is approximately 12 weeks
Additional design and modifications required to expand to other bus types

## Slide 14: Questions